## Charleston
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
CHARLESTON
| 1 | Town Hall | 5000 | 5/2024 | CIF | Public Works
| 2 | Park Improvements | 5000-8000 | 6/2024 | CIF | Public Works
| 1 | Road Repair & Maintenance | undetermined | 5/2024 | CIB/CIF | Bennett Constr. & Public Works
| 1 | Trails | 50000 | 5/2024 | undertermined | Publc Works
| 1 | Town Hall Roof | undetermined | CIF |  | undetermined

## Coalville
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
COALVILLE
| 1 | Culinary and Secondary Water Master Plan and Impact Fee Update | 200000 | 2023 | City Funds/DDW/CIB | Mayor/City Council/City Staff | $100,000 Planning Grant | 2023-02-01
| 2 | Wastewater Master Plan and Impact Fee Update | 150000 | 2023 | City Funds/ DWQ/CIB | Mayor/City Council/City Staff | $75,000 Planning Grant | 2023-06-01
| 3 | Irrigation Pond Lining | 800000 | 2023 | City Funds/DDRe Loan/CDBG | Mayor/City Council/City Staff
| 4 | South Lift Station/Force Main | 1325790 | 2023 | USDA/City Funds | Mayor/City Council/City Staff
| 5 | Culinary Water Lines on 200 Noth and Center St from approximately 60 W. | 300000 | 2023 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff
| 6 | Other Storm Drain Needs | 300000 | 2024 | City Funds/ CDBG | Mayor/City Council/City Staff
| 7 | Street Improvement Projects | 200000 | 2024 | City Funds | Mayor/City Council/City Staff
| 1 | Storm Drains | 500000 | 2024 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff
| 2 | Sidewalk Replacement | 500000 | 2025 | City Funds/Safe Routes to School/CDBG | Mayor/City Council/City Staff
| 3 | Improve Entrances into the City and Other Major Travel Corridors. | 250000 | 2025 | City Funds/CDBG/TA | Mayor/City Council/City Staff
| 4 | Community Trail Project | 500000 | 2026 | State Parks/UDOT Enhancement | Mayor/City Council/City Staff
| 5 | Pedestrian Bridge over I-80 | 1000000 | 2026 | RAP/City Funds/LWCF/Other Private Funds | Mayor/City Council/City Staff
| 1 | Storm Drain Upgrades | 2300000 | 2030 | Storm Drain Fees | Public Works
| 2 | Becon Hill Drive New Street Alignment | 1200000 | 2030 | Non-Urban UDOT/City B & C Funds | Public Works
| 3 | Multiple Street Widening Projects | 3400000 | 2030 | Looking for Funds/May Have to Bond on B&C Road Funds | Public Works
| 1 | Culinary and Secondary Water Master Plan and Impact Fee Update | 200000 | 2023 | City Funds/DDW/CIB | Mayor/City Council/City Staff
| 1 | Wastewater Master Plan and Impact Fee Update | 150000 | 2023 | City Funds/ DWQ/CIB | Mayor/City Council/City Staff
| 1 | Irrigation Pond Lining | 350000 | 2023 | City Funds/DDRe Loan/CDBG | Mayor/City Council/City Staff
| 1 | South Lift Station/Force Main | 1325790 | 2023 | USDA/City Funds | Mayor/City Council/City Staff
| 2 | Storm Drains | 500000 | 2024 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff
| 3 | Water System Upgrades | 300000 | 2025 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff
| 4 | Street Improvement Projects | 200000 | 2025 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff
| 5 | Sidewalk Replacement | 500000 | 2025 | City Funds/CDBG/Grants and Possible Loans | Mayor/City Council/City Staff

## Daniel
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
DANIEL
| 1 | Sewer Replacement | 173629 | 07/01/2023 | Taxes, Licenses, Interest $56,796 | Engineering
| 1 | N/A
| 1 | N/A
| 1 | Sewer Replacemenr | 173629 | 07/01/2023 | Storm Haven

## Francis
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by: | Scott Kettle
[6 empty] | Medium Term: 5 Years | Date Updated: | 2023-12-14
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
FRANCIS
| 1 | Water Improvements | 450000 | 2024 | CDBG, Water fund | Water
| 2 | City Hall and Council Chambers | 2500000 | 2024 | General Fund | General Fund
| 3 | Pave Wild Willow Park | 168000 | 2024 | UDOT TAP grant, General Fund | General Fund
| 4 | Drinking Water Source | 500000 | 2023-2024 | Water Impact Fees, Water fund | Water
| 5 | Upgrade Hallam Road Lift | 400000 | 2024 | Sewer Impact Fees, Sewer Fund | Sewer
| 6 | Upgrade Foothill Lift Station | 350000 | 2024 | Developer Contributions | Sewer
| 7 | Road Improvements | 300000 | 2024 | General Fund, SC Transportat Tax | Road
| 8 | Wild Willow Natural Playgroun d | 410000 | 2024 | Rap Tax, General Fund | Parks
| 1 | Park Improvments | 100000 | 2025 | Park Impact Fees, General Fund | Parks
| 2 | Community Center Upgrades | 100000 | 2025 | General Fund | Parks, Building
| 1 | NA
| 1 | Road Improvements | 200000 | Yearly | General Fund, SC Transportation Tax, B&C Roads | Roads
| 2 | Drinking Water Source | 500000 | 2024 | Impact Fees, CIB, Drinking Water, Water Resources | Water
| 3 | Drinking Water Storage Tank | 1500000 | 2024 | Impact Fees, CIB, Drinking Water, Water Resources | Water
| 4 | City Hall and Council Chambers | 2500000 | 2024 | General Fund | General Fund

## Heber
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
HEBER
| 1 | Land Purchase for Affordable Housing | 1000000 | 2024 | Local, CDBG, CIG | Planning
| 6 | Jordan Park (Red Ledges) ADA Soft Fall Surface | 65000 | 2023 | Impact Fees, Local, CIB, DP/Other | Cemetary and Parks |  | 2023
| 7 | Muirfield Park Expansion and Amenities | 3642000 | 2022 | Local, CIB, Impact Fees | Cemetary and Parks |  | 2024
| 8 | Main Street Park Amenities | $ - | 2022 | Local, CIB, Impact Fees | Cemetary and Parks
| 9 | Cemetary Phase 1 Expansion - Consultation Center and Cremation Phase | 2976000 | 2024 | Local, CIB, Impact Fees | Cemetary and Parks |  | 2022
| 10 | Coyote Park Construction | 1775000 | 2024 | Local, CIB, Impact Fees | Cemetary and Parks |  | 2022
| 11 | Parkview Place Park | 75000 | 2025 | Local, CDBG | Planning
| 12 | Wasatch Vista Park | 75000 | 2023 | Local, CDBG, Impact Fees | Planning
| 24 | I-028 Citywide PI Meter Replacements | 3406000 | 2024 | Impact Fees, DP/Other | Engineering
| 9 | I-029 Central Heber Irr Improvements - Phase 1 | 2769000 | 2024 | Local, impact Fees | Engineering
| 34 | P-073 Wasatch Vista Neighborhood Park (1.5 ac) | 186000 | 2024 | Impact Fees, DP/Other, CDBG | Engineering
|  | P-081 300 West Safe School Rte | 200000 | 2024 | Impact Fees, DP/Other | Engineering
| 43 | T-040 1200 East 1200 S Hwy 40 | 75000 | 2025 | Local, Impact Fees, DP/Other | Engineering
| 47 | P-054 2400 S Trail - Daniel Elem to Mill Rd | 389000 | 2022 | Impact Fees, DP/Other | Engineering
| 51 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 475000 | 2023-2024 | Local | Engineering
| 52 | T-061 Annual Sidewalk New Construction & Repair | 210000 | 2024 | Local | Engineering
| 54 | T-064 Intersection Align Hwy 40 and Mill Rd UDOT | 232000 | 2023-24 | Impact Fees, DP/Other | Engineering
| 60 | T-082 Annual Traffic Alming improvement | 800000 | 2025-28 | Local | Engineering
| 61 | I-001 Pressurized Irrigation Project - Central Heber | 528000 | 2024 | Impact Fees | Engineering
| 63 | W-008 1900 South - Hwy 40 to Mill Rd (12") | 109000 | 2025 | Impact Fees, DP/Other | Engineering
| 66 | W-035 700 North - Main St to 550 E | 290000 | 2022 | DP/Other | Engineering
| 68 | W-061 Hwy 40 - Coyote Ln to 850 N (12") | 343000 | 2022 | Impact Fees, DP/Other | Engineering
| 70 | W-067 500 East - 1200 S to Hwy 40 (8") | 331000 | 2022 | Impact Fees | Engineering
| 72 | W-071 Central Heber Wtr Replacements - Phase1 | 7275000 | 2022 | Local | Engineering
| 1 | D-015 Annual Ditch/Storm Drain Imp. | 890000 | 2023-2007 | Local | Engineering
| 2 | D-025 Storm Water Management Program | 335000 | 2025-2042 | Local | Engineering
| 3 | D-029 Main St to 600 S Ditch Replacement | 370000 | 2026 | Local | Engineering
| 4 | I-001 Pressurized Irrigation - Central Heber | 2112000 | 2023-2027 | Impact Fees | Engineering
| 5 | I-003 1200 W - 200 S to 650 S | 335000 | 2025 | Impact Fees, DP/Other | Engineering
| 6 | I-011 300 E - 800 N to Coyote Ln Canal Pipe (12") | 304000 | 2026 | Impact Fees, DP/Other | Engineering
| 7 | I-017 Annual Irrigation Main/Sys Replacements | 158000 | 2026-2028 | Local | Engineering
| 8 | I-028 Citywide PI Meter Replacements | 3406000 | 2025 | Local | Engineering
| 9 | I-029 Central Heber Irr Improvements - Phase 1 | 1267000 | 2025 | Local, Impact Fees | Engineering
| 11 | P-036 Center Creek Trail | 235000 | 2025 | Impact Fees, DP/Other | Engineering
| 12 | P-047 Duke Park (14.4 ac) | 1194000 | 2024 | Impact Fees | Engineering
| 13 | P-052 Park Equipment (various locations) | 130000 | 2026 | Impact Fees | Engineering
| 14 | P-053 1200 South Trail - 600 E to 1200 E * | 158000 | 2025 | Impact Fees, DP/Other | Engineering
| 15 | P- 054 2400 South Trail - Daniel Elem to Mill Rd | 104000 | 2027 | Impact Fees, DP/Other | Engineering
| 16 | P-055 Lower Wasatch Canal Trail and Bridge | 161000 | 2027 | Local, Impact Fees | Engineering
| 17 | P-060 IHC Trail - 1200 S to Hwy 40 | 185000 | 2025 | Local, Impact Fees | Engineering
| 18 | P-064 600 South Trail - Main St to 600 W | 149000 | 2023 | Local, Impact Fees | Engineering
| 19 | P-070 Coyote Springs Park | 2013000 | 2026 | DP/Other | Engineering
stopped | 21 | P-078 Master Plan Updates every 5 years (4 times) | 18000 | 2025 | Impact Fees | Engineering
| 22 | P-081 300 West Safe School Rte | 400000 | 2025-27 | DP/Other | Engineering
| 23 | S-025 Sage Br Spring Cr Canal - 300 N to 100 S (24") | 919000 | 2027 | Impact Fees | Engineering
| 24 | S-026 SR113 - 800 W to 930 W | 623000 | 2027 | Impact Fees | Engineering
| 25 | S-027 Sr113 - 930 W to Southfield Rd | 624000 | 2027 | Impact Fees | Engineering
| 26 | S-030 Annual Sewer Main/Sys Replacements | 1500000 | 2024-2028 | Local | Engineering
| 27 | S-035 Center Street - 800 E to 1300 E (8") | 441000 | 2024 | DP/Other | Engineering
| 28 | S-044 500 E - 1900 S | 73000 | 2026 | Impact Fees, DP/other | Engineering
| 29 | S-045 1200 South - 1000 E to 1200 E | 496000 | 2025 | Impact Fees, DP/Other | Engineering
| 30 | S-046 550 East - Valley Hlls Dr to 600 N (10") | 506000 | 2026 | Impact Fees, DP/Other | Engineering
| 31 | S-047 Central Heber Swr Replacements - Phase 1 | 4482000 | 2024-2025 | Local | Engineering
| 32 | T-041 Southfield Rd - 100 S to 1200 S | 729000 | 2026 | Local, Impact Fees, DP/Other | Engineering
| 33 | T-045 1200 South - 820 E to 1200 E * | 567000 | 2025 | Impact Fees, DP/Other | Engineering
| 34 | T-050 2400 South - 700 E to Hwy 40 * | 593000 | 2024 | Impact Fees, DP/Other | Engineering
| 35 | T-054 150 East - Coyote Lane to 700 N | 904000 | 2026 | Impact Fees, DP/Other | Engineering
| 37 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 1182000 | 2023-2027 | Local | Engineering
| 38 | T-061 Annual Sidewalk New Construction & Repair | 630000 | 2025-2027 | Local | Engineering
| 39 | T-063 Intersection Align Hwy 40 and 2400 S UDOT | 583000 | 2026 | Impact Fees, DP/Other | Engineering
| 40 | T-064 Intersection Align Hwy 40 and Mill Rd UDOT | 348000 | 2026 | Impact Fees, DP/Other | Engineering
| 41 | T-070 Downtown Parking - 400 N to 500 S (partial) | 126000 | 2025 | Impact Fees | Engineering
| 56 | T-069 1900 S to Mill Rd to 500 E | 482000 | 2026 | Impace Fees, DP/other | Engineering
| 42 | W-038 500 South - 300 W to Main St (8") * | 362000 | 2028 | Local, Impact Fees | Engineering
| 43 | W-041 Hwy 40 - 2200 S to 2400 S West (8") * | 178000 | 2026 | Impact Fees | Engineering
| 44 | W-043 Hwy 40 - 1300 S to 1700 S (8") | 128000 | 2026 | DP/Other | Engineering
| 45 | W-056 Annual Water Main/Sys Replacements | 2700000 | 2024-2027 | Local | Engineering
| 46 | W-061 Hwy 40 - Coyote Ln to 850 N (12") | 478000 | 2028 | Impact Fees, DP/Other | Engineering
| 47 | w-071 Central Heber Wtr Replacements - Phase 1 | 2436000 | 2043-2025 | Local | Engineering
| 2 | D-023 Master Plan Updates every 5 years (4 times). | 35000 | 2027-2042 | Local | Engineering
| 4 | I-014 Aerial Digital Map Updates (4 times) | 22000 | 2027-2041 | Impact Fees | Engineering
| 5 | I-015 Master Plan Updates every 5 years (4 times) | 267000 | 2029-2042 | Impact Fees | Engineering
| 6 | I-017 Annual Irrigation Main/Sys Replacements | 1077000 | 2029-2042 | Local | Engineering
| 7 | I-030 Central Heber Irr Improvements - Phase 2 | 5250000 | 2097-2042 | Impact Fees, DP/Other | Engineering
| 8 | I-031 Central Heber Irr Improvements - Phase 3 | 5250000 | 2029-2042 | Impact Fees | Engineering
| 9 | P-052 Park Equipment | 56000 | 2029-2042 | Impact Fees | Engineering
| 10 | P-055 Lower Wasatch Canal Trail and Bridge | 3000 | 2029-2042 | Local, DP/Other | Engineering
| 11 | P-078 Master Plan Updates every 5 years (4 times) | 55000 | 2029-2042 | Impact Fees | Engineering
| 12 | P-079 New Master Planned Trailheads | 1320000 | 2029-2042 | Impact Fees | Engineering
| 13 | S-020 Aerial Digital Map Updates (4 times) | 20000 | 2029-2042 | Impact Fees | Engineering
| 14 | S-021 Master Plan Update (4 times) | 220000 | 2029-2042 | Impact Fees | Engineering
| 15 | S-023 Hwy 40 - Center Cr Dr to 2200 S West (8") | 832000 | 2029-2042 | DP/Other | Engineering
| 16 | S-030 Annual Sewer Main/Sys Replacements | 2655000 | 2029-2042 | Local | Engineering
| 17 | S-048 Central Heber Swr Replacements - Phase 2 | 15500000 | 2029-2042 | Local | Engineering
| 18 | S-049 Central Heber Swr Replacements - Phase 3 | 15500000 | 2029-2042 | Local | Engineering
| 19 | T-040 1200 East - 1200 S to Hwy 40 * | 1189000 | 2029-2042 | Impact Fees, DP/Other | Engineering
| 20 | T-042 Master plan Update (4 times) | 203000 | 2029-2042 | Impact Fees | Engineering
| 21 | T-054 150 East - Coyote Lane to 700 N | 904000 | 2029-2042 | Impact Fees, DP/Other | Engineering
| 22 | T-060 Annual Rd Maint - Stripe, Seal, Overlay, Dips | 25975000 | 2029-2042 | Local | Engineering
| 23 | T-061 Annual Sidewalk New Construction & Repair | 3140000 | 2029-2042 | Local | Engineering
| 4 | I-1001 Pressurized Irrigation - Central Heber | 6241000 | 2029-2042 | Impact Fees | Engineering
| 63 | W-008 1900 S - Hwy 40 to Mill Rd | 154000 | 2029-2042 | Impact Fees, DP/Other | Engineering
| 24 | W-028 Master Plan Updates every 5 years (4 times) | 208000 | 2029-2042 | Impact Fees | Engineering
| 25 | W-029 Aerial Digital Map Updates (4 times) | 20000 | 2029-2042 | Impact Fees | Engineering
| 26 | W-056 Annual Water Main/Sys Replacements | 20630000 | 2029-2042 | Local | Engineering
| 27 | W-072 Central Heber Wtr Replacements - Phase 2 | 15500000 | 2029-2042 | Impact Fees | Engineering
| 28 | W-073 Central Heber Wtr Replacments - Phase 3 | 15500000 | 2029-2042 | Impact Fees | Engineering
| 1 | Land Purchase for Affordable Housing | 1000000 | 2022 | Local, CDBG, CIB
| 2 | Phase 1 of Downtown Water and Sewer Replacement | 24000000 | 2022 | Local, CIB, CDBG
| 4 | Traffice Improvement Study | 150000 | 2022 | Local, CIB
| 5 | Central Heber Pressureazed Irrigation Project | 7753000 | 2022 | Local, CIB |  |  | 2021-2040
| 6 | Muirfield Park Expansion | 3642000 | 2022 | Local, CIB, Impact Fees
| 7 | Cemetery Expansion Phase 1 | 2976000 | 2022 | Local, CIB, Impact Fees
| 8 | Citywide Fiber Installagtion | 21000000 | 2022 | Local, CIB, Bonds |  |  | 2022
| 9 | Wasatch Vista Park | 75000 | 2022-2025 | Local, CDBG, Impact Fees, CIB
| 10 | Jordan Park (Red Ledges) ADA Soft Fall Surface | 65000 | 2023 | Local, CDBG |  |  | 2023
| 11 | Irrigation Meter Project | 2346000 | 2025 | Local, CIB |  |  | 2021-2025
| 12 | West Side of Main Street Sidewalk 400 South to 500 South | 95000 | 2025 | Safe Sidewalk, Local Funds
| 13 | 910 S. Sidewalk from 100 West to 600 West (T061) | 80000 | 2025 | CDBG, Local Funds
| 14 | Western Truck Route | 100000000 | 2022 | Private, UDOT, City, County, CIB
| 15 | Downtown Improvements | 10000000 | 2022 | UDOT, CIB, Local
| 16 | Coyote Park | 200000 | 2025 | Local, CIB
| 17 | New City Hall | 5000000 |  | Local, CDBG, CIB, Bonds |  |  | 2025

## Henefer
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
HENEFER
| 1 | Secondary Water System | 5000000 | 2023 | DWRe/BOR/Town Funds | Town Council
| 2 | Town Hall Renovation/Community Center | 200000 | 2023 | ARPA/Town Funds | Town Council
| 3 | Culinary Water Well | 3000000 | 2024 | DWQ/CIB/Town Funds | Town Council
| 4 | Culinary Water Tank 650,000 gallon | 600000 | 2023 | Town Funds/DWQ/CIB | Town Council
| 5 | Wastewater Facilities Plan | $40,000 -$50,000 | 2023 | CDBG/CIB/DWQ | Town Council
| 6 | General & Land Use Ordinance Review and Update | 85000 | 2023 | Town Funds/UDOT/MAG/WFRC | Town Council
| 1 | Chip and Seal Roads | 180000 | 2023 | B&C Roads Funds | Town Council
| 2 | Watewater Lift Station | 100000 | 2025 | DEQ, CDBG | Town Council
| 3 | Cemetary Expansion | 250000 | 2026 | Town Funds | Town Council
| 1 | Replacing UV disinfection lights and retrofit of the building system for the wastewater | $250,000- $500,000 | 2025 | USDA/DEQ/CIB
| 1 | Secondary Water System | 5000000 | Fall 2023 | DWR/BOR/Town Funds
| 2 | General & Land Use Ordinance Review & Update | 85000 |  | Town Funds/UDOT/ MAG/WFRC
| 3 | Culinary Water Tank 650,000 | 600000 | Fall 2023 | DWQ/CIB/Town Funds
| 4 | Culinary Water Well | 3000000 | Summer 2024 | DWQ/CIB/Town Funds
| 5 | Town Hall Community Center | 200000 | Spring 2023 | ARPA/Town Funds
| 6 | Chip & Seal Roads | 180000 | Spring 2023 | B&C Road Funds
| 7 | Wastewater Facilities Plan | $40,000 - $50,000 | Spring 2023 | CDBG/CIB/DWQ
|  | Wastwater Lift Station | 100000 | Spring 2025 | DWQ/CDBG
|  | Cemetery Expansion | 250000 | Spring 2026 | Town Funds

## Hideout
Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by: | Jan McCosh
[5 empty] | Medium Term: 5 Years | Date Updated: | 2023-12-13
Long Term: 5-10 Years
Needs and Priorities
HIDEOUT
Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
1 | Heavy Equipment | 150000 | Q3 2024 | PCIFB | Public Works
2 | Trail Improvements | 250000 | Q3 2024 | Town/CDBG.PCI | Public Works
3 | Fencing for MTCE FAcility | 6000 | Q3 2024 | Grant with 7% match | Parks
4 | Chain Hoists | 6000 | Q3 2024 | Town | PUblic Works
5 | Trail maintenance equip | 3500 | Q3 2024 | Town/PCIFB | Planning
6 | Road Improvements | 100000 | Q3 2024 | PTIF | Public Works
7 | Infrastructure for Fire station | 650000 | Q1 2024 | Town/CDBG/PCI/FB | Public Works
1 | Purchase land for public parks | 1000000 | 2024 | Loan/Bond | Planning
2 | Pedestrian under/over pass | 3000000 | 2025 | Grant/UDOT | Public Safety
3 | Wildlife Fencing | 1000000 | 2025 | Grant/UDOT | Public Safety
4 | Culinary, sewer, storm drain | 150000 | 2026 | Grant/Town | Public Works
5 | Infrastructure for fire station | 2000000 | 2026 | Loan/Bond | PUblic Works

## Independence
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
INDEPENDENCE
| 1 | Center Creek Road 7 miles | 6500000 | 2024 | CIB/General Fund | Roads | 6500000 | 2023-06-01
| 2 | Center Creek Road 7 miles | 6500000 | 2024 | CDBG | Roads
| 3 | Highway 40 Frontage Improvements | 1000000 | 2025 | CDBG | Roads
4
5

## Interlaken
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
INTERLAKEN
1
1
1
1

## Kamas
| Capital Improvements Projects Summary 2024 | [5 empty] | Short Term: 1 Year | Updated by: | Scott Kettle
[7 empty] | Medium Term: 5 Years | Date Updated: | 2023-12-12
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts |  | Resp. Department | CIB Request Amount | CIB Submission Date
KAMAS
| 1 | Sewer Improvements | 350000 | 2024 | CDBG/Sewer
| 2 | Sewer Pond Cleaning | 250000 | 2024 | CDBG/Sewer
| 3 | City Hall Park Improvements | 150000 | 2024 | RAP Tax Grant, General Fund, and Summit Count
| 4 | City Hall Improvements Window Replacement | 6000 | 2024 | General Fund
| 5 | Emergency Management Plan | 10000 | 2024 | General Fund
| 6 | Beaver Creek Culvert Extension/Water Line Replacement | 215000 | 2024 | Water/Class C Road Funds/Road Impact Fees
| 1 | Road Repairs & Maintenance | 250000 | Yearly | General Fund/Class B
| 2 | City Hall Improvements Police Office Addition | 100000 | 2025 | General Fund
| 3 | Water Valves | 20000 | 2025 | CDBG/Water
| 4 | Left Hand Spring Improvements | 250000 | 2024 | Water
| 5 | Grassy Creek Park | 150000 | 2024 | Park Impact Fees, General Fund
| 6 | Sewer System Upgrade | 5000000 | 2026 |  | Sewer Fund/Impact Fees/DEQ
| 7 | Main Street Beautification | 1000000 | 2026 | CIB Loan/ Grants/ UDOT
| 8 | Center Street Beautification | 500000 | 2024 | CIB Loan/ Grants/ UDOT
| 1 | Park Development | 100000 | 2027 | CDBG, Impact Fees
| 2 | Center Street Bridge | 300000 | 2025 | Road Impact Fees/Class B Roads
| 1 | Complete Water System Upgrades as per Master Plan | $250,000/year | High | Impact Fees, CDBG
| 2 | Complete Sewer System Upgrades as per Master Plan | $250,000/year | High | Impact Fees, CDBG
| 3 | Road Resurfacing | $250,000/year | High | Class C Road Fund, General Fund
|  | Center Street Beautification | 500000 | Medium | CIB Loans, Grants, UDOT
| 4 | Main Street Beautification | 1000000 | Medium | CIB Loans, Grants, UDOT
| 5 | Study on Necessity of Storm Drain System | 50000 | Low | General Fund
| 6 | Purchase Maintenance Vehicles | 120000 | Low | General Fund

## Midway
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
MIDWAY FY2015 submission
| 1 | 2015 Road Projects | 370000 | Spring 2015 | General Fund, Impact Fees | Engineering/Public Works
| 2 | 2015 Water Projects | 974000 | Spring 2015 | General Fund, Impact Fees | Engineering/Public Works
| 3 | 2015 Road Surface Treatment | 100000 | Spring 2015 | General Fund | Engineering/Public Works
| 4 | Demo and Rebuild Fire Station | 1500000 | Summer 2015 | Wasatch County | Building Department
| 5 | Park Improvements | 70000 | Yearly | General Fund, Impact Fees | Public Works
| 6 | Building Improvements | 50000 | Yearly | General Fund | Building Department
| 1 | Road Projects | 1820000 | Yearly | General Fund, Impact Fees | Engineering
| 2 | Water Projects | 3845000 | Yearly | General Fund, Impact Fees | Engineering
| 3 | Park Improvements | $70,000/year | Yearly | General Fund, Impact Fees | Public Works
| 4 | Building Improvements | $50,000/year | Yearly | General Fund | Building Department
| 5 | Homestead Trail | 1000000 | 2016 | Trail IF, Grants | Engineering
| 1 | Road Projects | $250,000/year | Yearly | General Fund, Impact Fees | Engineering
| 2 | Water Projects | $350,000/year | Yearly | General Fund, Impact Fees | Engineering
| 3 | Park Improvements | $70,000/year | Yearly | General Fund, Impact Fees | Public Works
| 4 | Building Improvements | $50,000/year | Yearly | General Fund | Building Department
| 1 | Improved Mapping System | 200000 | Unknown | General, Unknown
| 2 | Improved SKADA System | 75000 | Unknown | General, Unknown
| 3 | Upgrade Culinary Meter System | 300000 | Unknown | General, Unknown
| 4 | Create a Storm Drain System | 3000000 | Unknown | General, Grant, Unknown
| 5 | Improve the Midway Trial System |  | Unknown

## Oakley
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
OAKLEY FY2016 submission
| 1 | Screens for the Sewer Plant | 165000 | April 2016 | General Fund | Sewer
| 1 | Well |  |  |  | Water

## Park City
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
PARK CITY
| 1 | Senior Community Center | $3,500,00 | 2024 | CIP Fund, Lower Park RDA, CDBG | Housing
| 2 | Public Art | 560431 | 2024 | CIP Fund, Lower Park RDA | Special Events
| 3 | Traffic Calming Study | 202856 | 2024 | Lower Park RDA | Transportation
| 1 | Bus Shelter Design and Capital Impro | 15485888 | 2024 | Transit Fund | Transportation
| 2 | Rec Building in City Park | 15241042 | 2025 | Fund, Lower Park RDA | Recreation
| 3 | PC MARC Aquatics Enhancements | 6000000 | 2025 | CIP Fund | Recreation
| 4 | Land Acquisition/Banking Program | 750000 | 2025 | Fund, Lower Park RDA | Housing
| 1 | Housing Program Public Private Part | 17000000 | 2024 | CIP Fund | Housing
| 2 | Transit Rolling Stock Replacements | 16185946 | 2024 | Transit Fund | Transportation
| 3 | Houisng Program Asset Acquistion | 5500000 | 2024 | CIP Fund | Housing
| 4 | Housing Ongoing Asset Improvement | 1980299 | 2024 | Fund, Lower Park RDA | Housing

## Summit County
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by: | Annette Singleton
[6 empty] | Medium Term: 5 Years | Date Updated: | 2023-12-14
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
SUMMIT COUNTY
| 1 | Wanship Water Company | 2000000 | 2024, ongoing | Community Assessment/CDBG | CDD, Council/Manager
| 2 | Silver Creek to Bitner Road Connection | 7400000 | 2024 Ongoing | Municipal/Capital/ TST | Public Works
| 3 | Street Lighting | 100000 | 2024 Ongoing | Municipal/Capital | Public Works
| 4 | Frontage Rds Repaving | 1160000 | 2024 | Municipal/Capital | Public Works
| 5 | Weber Canyon Bridge Replacement | 150000 | 2024 | Municipal/Capital | Public Works
| 6 | Pinebrook Roads Recon | 330000 | 2024
| 7 | Bearhollow Dr Repaving | 450000 | 2024
| 1 | Old Ranch Road Reconstruction | 750000 | 2023-2024 | Municipal/Capital | Public Works
| 2 | Acquire open space through Eastern Summit County Agriculture Preservation Committee | 1400000 | Ongoing | ESAP fund | CDD
| 3 | Acquire Open Space through Basin Open Space Advisory Committee | 4000000 | Ongoing | Bond | Council/Manager
| 4 | Upgrades to the Snyderville Basin Water Reclamation District due to growth | 9000000 | Ongoing | Bond | Council/Manager
| 5 | Rural Water Association of Utah – Code updates regarding water system standards |  | Ongoing |  | CDD
| 6 | Hoytsville Road Shoulder Widening & Intersection | 1000000 | 2022-2026 | Municipal/Capital | Public Works
| 7 | Chalk Creek Road Recon. | 500000 | 2022, ongoing | Service Area 8 | Public Works
| 8 | Land acquisition for cemetery expansion | 200000 | 2013 | Municipal/Capital | Admin
| 10 | SR-32 Multi Use Trail | 852000 | 2024 | Municipal/Capital | Public Works
| 11 | County Facilities expansion plan; | 27000000 | 2023-2025 | GO/MBA Bonds | Facilities
| 12 | SR-224 Off-Grade Pedestrian Crossing | 3000000 | 2025 | SBSRD/Municipal/ Capital | Public Works
| 13 | US 40 Frontage/SR-248 Intersection | 2925000 | 2025 | Municipal/Capital | Public Works
| 15 | Highland Drive Repaving | 850000 | 2024 | Municipal/Capital | Public Works
| 16 | SR-224 BBT | 40000000 | 2023-2026 | TST | Transportation

## Wallsburg
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by: | Alisha O'Driscoll
[6 empty] | Medium Term: 5 Years | Date Updated: | 2023-11-01
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
WALLSBURG FY2024 submission
| 1 | Wallsburg Town Water System Distribution Line | 7000000 | Spring 2024 | 51% DDW Grant/49% Loan | Water
| 1 | Town Council Chambers Remodel | unknown | Various | Unknown | General
| 1 | Wallsburg Town Park Trail | $350,00 | May 2024 | Grant with 7% match | Parks
| 2 | Road Repair | 1000000 | Ongoing | Unknown | Roads

## Wanship
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
WANSHIP
1
2
1
1

## Wasatch County
| Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[6 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
| Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
WASATCH COUNTY
| 1 | Senior Citizen Housing | 2000000 | 7/31/2021 | CDBG, HUD, FMHA, USDA Rural Dev., WCHA, MAG | County Manger
| 2 | Road Shop at Jordanelle | 3000000 | 4/1/2021 | General Fund, B&C Roads, Mineral Lease | County Manager
| 3 | Roads | 1000000 | 4/1/2021 | B&C Road Funds, Mineral Lease | Roads Department
| 4 | Equipment (Roads, Solid Waste, Senior Citizens, and Motor Pool | 1400000 | 4/1/2021 | PCIB, General Fund, CDBG | County Council, County Manager
| 5 | Solid Waste Facilities Expansion | 2500000 | 7/1/2021 | PCIB, 54-Fund Budget | County Council
| 6 | Flood Control | 200000 | 3/1/2021 | City and County General Funds | City and County Councils
| 1 | Public Safety/Road Shops at Strawberry | 2000000 | 1/1/2022 | Fire District, B&C Roads, Mineral lease | City and County Councils
| 2 | Road and Buildigns | 4000000 | 4/1/2022 | B&C Road Funds, CIB, General Fund | County Manager, Public Works
| 3 | Senior Citizens, Mental Health Housing & ADA Ramp at Admin Building | 2000000 | 6/1/2022 | CDBG, HUD, FMHA/Rural Dev., WCHA | County Manager, Public Works
| 4 | Flood Control | 500000 | 10/1/2022 | General Funds, Mitigation Grants | City and County Councils, County Manager
| 1 | Roads | 10000000 | 1/1/2025 | B&C Road, CIB, General Fund | County Manager, Public Works
| 2 | Equipment | 2000000 | 1/1/2025 | B&C Road, CIB, General Fund | County Manager, Public Works
| 3 | Administration Building | 12000000 | 1/1/2025 | Revenue Bond, CIB, Sales Tax, G.O.Bond | City and County Councils, County Manager
| 1 | Senior Citizens Housing | 2000000 | 7/31/2021 | CDBG, HUD, FMHA/Rural Dev., WCHA, MAG
| 2 | Road Shop at Jordanelle | 3000000 | 4/1/2021 | General Fund, B&C Roads, Mineral Lease
| 3 | Roads | 10000000 | 4/1/2025 | B&C Road Funds, Mineral Lease, General Fund
| 4 | Equipment (Roads, Solid Waste, Senior Citizens, Motor Pool) | 1400000 | 4/1/2021 | CIB, General Fund, CDBG

## Sheet2
Capital Improvements Projects Summary 2024 |  |  |  |  | Short Term: 1 Year | Updated by:
[5 empty] | Medium Term: 5 Years | Date Updated:
Long Term: 5-10 Years
Needs and Priorities
Rank | Project Description | Total Est. Cost | Est. Start Date | Revenue Source/Amounts | Resp. Department | CIB Request Amount | CIB Submission Date
1
2
3
4
5
1
1
2
3
4